## Sheet1
Story ID | Story Name | Description (User Story) | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation（Story Points） | Notes | Date started (planned) | Date finished (planned)
AD001 | System User Management | As a system admin, I want to create, edit and delete TA/MO accounts, so that I can control the access rights of all system users and ensure data security. | high | 1 | 1. Administrators can search for specific accounts using a unique identifier. 2. Administrators can create, edit, or delete accounts. 3. Administrators can batch create, delete, or disable accounts. 4. A secondary confirmation prompt is displayed when deleting or disabling an account to prevent accidental operations. | 5 | Only the admin has this permission; no access entry for MO/TA | 2026-03-27 | 2026-04-12
AD002 | TA Workload Overview | As a system admin, I want to view the overall workload of each TA (including applied/assigned jobs), so that I can grasp the TA resource allocation status and avoid overloading. | very high | 1 | 1. Administrators can filter workloads by TA name, student ID, position type, and time range. 2. Visualize TA work status, quantity, and working hours. 3. Support unified export of workload data. 4. View detailed position information for individual TAs. | 2 | Unified Workload Standards | 2026-03-27 | 2026-04-28
AD003 | TA Workload Balancing | As a system admin, I want the system to automatically balance the TA workload and give allocation suggestions, so that I can optimize the TA resource allocation and ensure fair assignment. | very high | 1 | 1. The system can set a maximum workload threshold for individual TAs. 2. When workload exceeds the threshold, the system automatically triggers a red alert. 3. Upon red alert activation, the system recommends alternative candidates to the MO and notifies the TA of workload excess. 4. Administrators can manually adjust system workload balancing. | 8 | Relies on AD002 basic data query | 2026-03-27 | 2026-04-28
AD004 | Job Post Approval | As a system admin, I want to review and approve/reject the jobs posted by MOs, so that I can ensure the rationality of the posted jobs and control the overall recruitment demand. | very low | 1 | 1. Positions published by MOs are automatically submitted to administrators for review. 2. Administrators can view position details. 3. Approved positions are displayed on the system; rejected positions are returned to the MO with review comments. 4. Support batch review of positions. 5. Support filtering positions by MO name or position type. | 4 | Advanced AI Review | 2026-04-27 | 2026-05-05
AD005 | System Operation Log View | As a system admin, I want to view all system operation logs (user login/ job publish/ application submit), so that I can trace abnormal operations and conduct problem investigation. | low | 1 | 1. Log content includes operator, operation time, operation details, IP address, and operation result. 2. Logs can be filtered by operation type, operator, and operation time. 3. Support log data export. | 4 | Automatic log collection based on basic system operations | 2026-04-28 | 2026-05-05
AD006 | TA Skill Library Management | As a system admin, I want to add, edit and delete the skill tags in the system, so that the AI can accurately match the job and TA skills based on the standard skill library. | very high | 1 | 1. Skill tags are categorized by type. 2. Administrators can add, edit, or delete skill tags. 3. When deleting a tag in use, it can be replaced with another tag. 4. Administrators can batch import and export tags. | 7 | Provide a standard tag library for TAs and MOs to select from | 2026-03-28 | 2026-04-30
AD007 | Recruitment Process Status Management | As a system admin, I want to start/end the recruitment period for different job types, so that I can control the overall TA recruitment progress of the school. | medium | 1 | 1. Set recruitment start and end times by position type. 2. Upon recruitment end, the system automatically closes the application portal, preventing TAs from submitting applications. 3. If recruitment ends early or is extended, the system sends notifications to TAs and MOs. 4. Visual display of current recruitment status for each position type. | 5 | Recruitment status changes are synchronized to MO's job post page and TA's job seek page | 2026-04-20 | 2026-04-28