## Sheet1
Story ID | Story Name | Description (User Story) | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation（Story Points） | Notes | Date started (planned) | Date finished (planned)
AD001 | System User Management | As a system admin, I want to create, edit and delete TA/MO accounts, so that I can control the access rights of all system users and ensure data security. | high | 1 | 1. The admin can query/edit basic user info (name, ID, role) by unique account ID | 5 | Only the admin has this permission; no access entry for MO/TA | 2026-03-27 | 2026-04-12
2. Support batch creation of MO/TA accounts and single account disable/enable/delete
3. Pop up a secondary confirmation prompt when deleting/disabling an account
4. Automatically retain all user operation records with operator and operation time
AD002 | TA Workload Overview | As a system admin, I want to view the overall workload of each TA (including applied/assigned jobs), so that I can grasp the TA resource allocation status and avoid overloading. | very high | 1 | 1. Support filtering workload by TA name/ID, job type (module TA/invigilation), and time range | 2 | Relates to TA's job application and MO's selection result data | 2026-03-27 | 2026-04-12
2. Display the number and working hours of TA's completed/ongoing/pending jobs in a visual table
3. Support exporting workload data as CSV/JSON format
4. View the detailed job info and assigned MO of a single TA
AD003 | TA Workload Balancing | As a system admin, I want the system to automatically balance the TA workload and give allocation suggestions, so that I can optimize the TA resource allocation and ensure fair assignment. | very high | 1 | 1. The system can set a maximum workload threshold for a single TA | 8 | AI-based workload matching function, relies on AD002 basic data query | 2026-03-27 | 2026-04-12
2. Pop up a red alert and recommend alternative TAs when TA's workload exceeds the threshold
3. Support the admin to manually adjust the workload balancing rules
4. Export alert info and send it to the corresponding MO
AD004 | Job Post Approval | As a system admin, I want to review and approve/reject the jobs posted by MOs, so that I can ensure the rationality of the posted jobs and control the overall recruitment demand. | very low | 1 | 1. Jobs posted by MOs go online only after admin's approval | 4 | MOs without review permission have posted jobs in "pending" status, invisible to TAs | 2026-03-27 | 2026-04-12
2. The admin can view job details (requirements, working hours, quantity) and fill in review comments
3. Approved jobs go online automatically; rejected ones are returned to MO with modification reasons
4. Support batch job review and filter pending jobs by MO name/job type
AD005 | System Data Management | As a system admin, I want to back up, restore and clean the system data (user/ job/ application), so that I can prevent data loss and keep the system data clean and effective. | very low | 1 | 1. Support manual/auto backup of all system data in JSON/CSV format | 2 | Auto backup is set to 24:00 daily by default; admin can modify the frequency | 2026-04-03 | 2026-04-12
2. Restore data by selecting backup files from a specified time node
3. Support cleaning expired data
4. Record logs for all data backup/restore/clean operations for traceability
AD006 | System Operation Log View | As a system admin, I want to view all system operation logs (user login/ job publish/ application submit), so that I can trace abnormal operations and conduct problem investigation. | low | 1 | 1. Support filtering logs by operation type, operator, operation time, and operation result (success/failure) | 4 | Automatic log collection based on basic system operations, no additional data entry | 2026-04-04 | 2026-04-12
2. Logs include operator, time, content, IP address and result
3. Log data supports export and cannot be modified/deleted
4. Support paginated log display and sort in reverse chronological order
AD007 | TA Skill Library Management | As a system admin, I want to add, edit and delete the skill tags in the system, so that the AI can accurately match the job and TA skills based on the standard skill library. | very high | 1 | 1. Support adding/editing/deleting skill tags | 7 | Provide standard tag library for AI skill matching, link with TA CV upload and MO job post functions | 2026-03-28 | 2026-04-12
2. Classify skill tags by category (professional/general skills, work experience)
3. Pop up a prompt when deleting used skill tags, support replacing with other tags
4. Support batch import/export of skill tags
AD008 | Recruitment Process Status Management | As a system admin, I want to start/end the recruitment period for different job types, so that I can control the overall TA recruitment progress of the school. | medium | 1 | 1. Set recruitment start/end time by job type (module TA/invigilation) | 5 | Recruitment status changes are synchronized to MO's job post page and TA's job seek page | 2026-04-05 | 2026-04-12
2. The system automatically closes the application entry for corresponding jobs after recruitment ends, TAs cannot submit applications anymore
3. Support early ending/extending the recruitment cycle, send notifications to all MOs/TAs after operation
4. Display current recruitment status (ongoing/ended/not started) of each job type on the system homepage