## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
Story1 | TARegistration | As a student, I want to register an account with my name, email and password, So that I can access the TA recruitment system and apply for positions. | Must | 2 | 1. The email must match the standard pattern: [a-zA-Z0-9._%+-]+@[a-zA-Z0-9.-]+\.[a-zA-Z]{2,}$. 2. The password must be between 6 and 8 characters long and must contain at least one letter and one number. 3. The password must not be identical to the user's email address. 4. The user name must contain only letters, spaces, or underscores and must not exceed 12 characters in length. 5. The system must display a clear error message for any input that fails to meet the specific format requirements. 6. The system must save valid user records to the database and automatically redirect to the Login page upon success. | 3 | When reviewing at the code level, attention should be paid to the format. | 4.23 | 4.25
Story2 | TALogin | As a TA, I want to log in with my email and password, So that I can access the TA system and use its features. | Must | 2 | 1. The system must verify that the email exists in the local data file and is associated with the 'TA' role. 2. The system must check if the provided password matches the record retrieved from the local storage file. 3. The system must display a clear error message if the credentials do not match any local record or if the fields are empty. 4. The system must create a valid user session in memory and redirect to the TA Dashboard upon successful authentication. | 3 |  | 4.26 | 4.28
Story3 | ApplicantProfile | As a TA, I want to create and save my applicant profile including my GPA and skills, So that recruiters can review my qualifications for TA positions. | Must | 2 | 1. The system must provide input areas for personal information, academic background, internship experience, activities, and skills. 2. The interface should offer placeholders or labels to guide users to describe their background from multiple perspectives without mandatory constraints. 3. The system must allow the TA to save the profile even if some sections, such as internships or activities, are left blank. 4. The system must associate the profile content with the logged-in user's unique identifier in the local storage file. 5. The system must ensure that the profile data is correctly written to a local text-based file and can be retrieved later for review. | 2 |  | 4.29 | 4.3
Story4 | CVUploader | As a TA, I want to upload my CV in PDF format, So that my application documents are stored in the local system for the recruiter's review. | Must | 2 | 1. The system must allow the user to select a local file via a file browser interface. 2. The system must restrict the uploaded file type to the PDF format only. 3. The system must copy the selected file to a designated local storage folder within the project directory. 4. The system must rename the uploaded file or link its local path to the user's email to ensure unique identification. 5. The system must display a success message once the file transfer to the local repository is complete. | 5 |  | 5.1 | 5.5
Story5 | JobDiscover | As a TA, I want to browse all available TA positions, So that I can find a role that matches my background and interests. | Must | 3 | 1. The system must read all available job records from the local data file and display them in a list view. 2. Each job entry must display essential details such as the module name, responsibilities, and application deadline. 3. The system must only show jobs that have not yet reached their application deadline based on the system date. 4. The user must be able to view the full details of a specific job by selecting it from the list. 5. The system must display a notification if no available jobs are found in the local storage records. | 3 |  | 5.6 | 5.8
Story6 | JobApplication | As a TA, I want to submit an application for a specific job, So that my interest is formally recorded for the recruiter's review. | Must | 3 | 1. The system must allow the user to click an "Apply" button on a selected job detail page. 2. The system must prevent a user from applying to the same job multiple times by checking existing local records. 3. The system must automatically link the current user's email with the unique Job ID in the local application file. 4. The system must display a success message confirming that the application has been successfully saved to the local file. | 5
Story7 | ApplicationStatus | As a TA, I want to check the status of my submitted applications, So that I can see if I have been accepted or rejected. | Must | 3 | 1. The system must filter the local application file to retrieve only the records belonging to the logged-in user. 2. The system must display the current status of each application, such as "Pending", "Accepted", or "Rejected". 3. The system must automatically refresh and display the latest status updated by the recruiter in the local data file. 4. The system must inform the user if they have not submitted any applications yet. | 3