## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
story1 | PostTAPosition | As an MO, I want to post TA positions for my activities, so that TAs can view them and apply. | Must | 2 | 1. After successfully logging into the system, the MO can enter the “Post Position” page. 2. The MO can create a new TA position. 3. The published position will be displayed in the position list. 4. TA users can view the position information in the system. 5. TA users can submit applications for published positions. | 3 |  | 4.5 | 4.1
story2 | PositionDetails | As an MO, I want to fill in job details, such as the activity name, job responsibilities, required skills, number of positions, and application deadline, so that applicants can clearly understand the role and its requirements. | Must | 2 | 1. The MO can enter the activity name when creating a position. 2. The MO can enter the job responsibilities when creating a position. 3. The MO can enter the required skills when creating a position. 4. The MO can enter the number of positions needed when creating a position. 5. The MO can set the application deadline when creating a position. 6. If all required information is not completed, the system shall not publish the position successfully and shall display a prompt indicating the missing information. 7. After the position is published, applicants can view all of the above detailed information about the position. | 2 | The activity name, responsibilities, number of positions, and application deadline should be mandatory fields. | 4.1 | 4.16
story3 | EditPosition | As an MO, I want to edit published positions, so that I can modify the activity details, deadline, or update the recruitment requirements. | Must | 2 | 1. The MO can open the edit page for a position they have already published. 2. The MO can modify the activity details. 3. The MO can change the application deadline. 4. The MO can update the recruitment requirements, such as required skills or the number of positions. 5. After saving, the system shall display the updated position information. 6. The updated position information shall also be shown on the TA page at the same time. | 3 | Published positions can only be edited before the application deadline or before the recruitment is closed. | 4.17 | 4.25
story4 | ApplicantProfile | As an MO, I want to view the profiles and CVs of each TA who applies for the position, so that I can judge whether the TA is suitable for the role. | Must | 2 | 1. The MO can view all TAs who have applied for the position in the applicant list. 2. The MO can click on a TA to view their profile. 3. The MO can view the TA’s CV and personal information. 4. The TA’s basic information shall include at least their name, contact details, relevant background information, and personal skills. 5. If a TA has not uploaded a CV, the system shall clearly display “No CV available.” 6. The MO can only view information of TAs who have applied for the position and cannot freely access the profiles of other TAs. | 5 |  | 4.26 | 5.1
story5 | CVList | As an MO, I want the system to provide a CV list interface where I can directly view applicants’ CVs, so that I can directly send the corresponding offer to the TA. | Must | 2 | 1. The system shall display all TAs for a position in a CV list interface. 2. The MO shall be able to view each applicant’s CV directly from the list. 3. The CV list shall display key TA information, such as name and contact details. 4. The MO shall be able to select a TA from the list and directly issue an offer. 5. After an offer is sent, the system shall automatically update the TA’s application status. 6. The selected TA shall receive a notification after the offer is issued. | 5 |  | 5.2 | 5.8
story6 | ApplicationStatus | As an MO, I want to update the application status of applicants, so that TAs can know whether they have been rejected or accepted. | Must | 3 | 1. The MO can view the current application status of each TA in the applicant list. 2. The default status of a TA shall be “Pending.” 3. The MO can change the application status to “Accepted” or “Rejected.” 4. After the status is updated, the system shall save the latest result. 5. After logging in, the TA can view their latest application status. 6. Each application can only have one status at a time. 7. If the status update fails, the system shall display an error message and allow the MO to resubmit. | 3 |  | 5.8 | 5.12
story7 | TASummary | As an MO, I want to view a summary of the TAs recruited for each activity, so that I can better arrange activity tasks. | Must | 3 | 1. The MO can view the list of accepted TAs for the activity. 2. The system shall display the corresponding accepted TAs by activity. 3. Each summary record shall include at least the TA’s name and basic information. 4. The MO can view the accepted TAs for different activities separately. 5. The summary information shall remain consistent with the latest acceptance results. 6. If no TA has been accepted for an activity, the system shall display a clear prompt. | 3
story8 | CloseRecruitment | As a MO, I want to cancel recruitment information for activities that have already ended, so that TAs will not apply for positions that are no longer available. | Must | 2 | 1. The MO can perform the “Close Recruitment” action for positions related to completed activities. 2. After a position is closed, it shall be removed from the application list or marked as “Closed.” 3. TAs shall no longer be able to submit new applications for closed positions. 4. The system shall retain the historical record of the position for future reference. | 3